Contoso General Assurance Indonesia

Steering Committee Brief (raw notes)

For the Q3 2026 CIPM Steering Committee, 17 Jul 2026

Author: Rina Halim, PMO. Reviewer: Budi Santoso, CTO. Status: DRAFT, not yet formatted.

__________________________________________________________________________________________

Purpose of this note

These are the raw bullet notes from the pre-steering huddle held on 15 Jul 2026. They are captured here for Copilot to turn into a polished, board-ready deck. Nothing in this document has been styled, sequenced or fact-checked with the finance team.

1. Where we are

Wave 2 amber, on the back of marine cargo UAT slippage.

Property and motor modules green, both on track to go live in Jul.

Broker portal live with 8 pilot brokers, positive early feedback especially from PT Mandiri Sinar Broker.

Data cleansing exceeded target: duplicate customers down from 4.2 percent to 0.7 percent.

Cyber and IAM: SSO complete, privileged access review upcoming.

Change: 72 percent of underwriters trained, 44 percent of claims adjusters trained, comms plan active.

2. What we want to say about marine cargo

Root cause of slippage is the endorsement calculation engine, which was underspecified in the original SOW.

14 open defects, of which 3 are severity 1. Vendor has assigned two additional developers.

Realistic go live date is 13 Sep 2026, a 21 day slip.

The Sep date avoids collision with the property renewal peak in Oct.

Hyper-care will run for six weeks post go live rather than the standard four weeks.

3. Financials headline

58 percent of budget spent against 58 percent of plan elapsed.

Contingency draw is only 24 percent, healthy buffer.

Requesting reallocation of IDR 1.2 bn from training contingency into UAT capacity.

No change to total programme envelope requested.

4. Regulatory and compliance

OJK is introducing a sharia line designation in the SIPP monthly return, effective Aug 2026.

This needs a small schema change in the new platform and a re-run of the historic 24 month migration.

We propose a parallel run for the Aug submission to de-risk.

Legal has confirmed no personal data protection impact from the schema change.

5. Stakeholder heat

Head of Marine Underwriting is frustrated by the delay, especially given cargo volumes trending up.

Bancassurance partners (BCA, Mandiri) have been briefed on the go live sequence.

Leasing partners (BCA Finance, Mandiri Tunas Finance) want early access to the new motor endorsement API.

Manufacturers (Astra International, MMKI) are watching the API contract carefully.

Regulator OJK: on track for Aug submission, no escalations.

6. Asks of the Steering Committee

Approve revised marine cargo go live of 13 Sep 2026.

Approve reallocation of IDR 1.2 bn within the approved envelope.

Endorse parallel run for the OJK SIPP Aug submission.

Note the vendor delivery lead succession plan (to be tabled at the Aug steering).

7. What we are not covering today

Wave 3 scoping (health and sharia lines): separate paper in Aug.

Contact centre modernisation: separate governance under COO.

Data platform migration: separate CIO programme.

8. Suggested deck outline (for Copilot to draft)

Slide 1 — Cover: title, date, author, classification.

Slide 2 — Executive summary in five bullets.

Slide 3 — RAG dashboard by workstream.

Slide 4 — Milestone timeline with marine cargo slip called out.

Slide 5 — Marine cargo deep dive.

Slide 6 — Financials and contingency utilisation.

Slide 7 — Regulatory and compliance update.

Slide 8 — Stakeholder heat map.

Slide 9 — Asks of the Steering Committee.

Slide 10 — Appendix: risks, decisions log, next steering date.