## RAID Log
ID | Category | Title | Description | Owner | Severity | Status | Raised Date | Due Date | Mitigation
R001 | Risk | Motor Platform data migration slippage | Legacy motor policy master data has inconsistent VIN and chassis references across two source systems on the Motor and Property Claims Platform Modernisation programme. | Budi Prasetyo | High | Open | 2026-01-12 | 2026-02-28 | Data cleansing squad on-boarded; daily reconciliation dashboard live from week 6.
R002 | Risk | Property fire claims spike, monsoon season | Historic loss data shows Property Fire claims volume rises 40 percent during Jan to Mar. Adjuster capacity in Jakarta and Surabaya may lag. | Sari Wulandari | High | Open | 2026-01-15 | 2026-03-15 | Cross-train 12 motor adjusters on property FNOL by end Feb; standby panel of external loss adjusters agreed.
I001 | Issue | Marine Cargo policy issuance API failing at broker onboarding | Marine Cargo Digital Onboarding platform is throwing 500 errors when three tier-1 brokers submit bulk endorsements. | Andi Nugroho | High | Open | 2026-02-02 | 2026-02-20 | Vendor hotfix scheduled for 2026-02-18. Interim manual path in place with SLAs to broker desk.
D001 | Dependency | Bancassurance partner sandbox availability | Bancassurance Distribution Integration requires two partner banks to provide sandbox tokens. Bank BCA Syariah has responded, Bank Mandiri has not. | Rina Kartika | Medium | Open | 2026-01-20 | 2026-02-25 | Escalation letter from CTO to Bank Mandiri Head of Digital Channels sent 2026-02-05.
A001 | Assumption | Sharia product pricing table stable through UAT | Sharia Product Launch assumes actuarial tables signed off by the DSN advisor will not change through UAT (mid Feb to end Mar). | Dewi Anggraini | Medium | Open | 2026-01-08 | 2026-02-15 | Weekly sync with DSN advisor booked. Pricing change control board convened if any update required.
R003 | Risk | Auto Manufacturer partnership API scope creep | Auto Manufacturer Partnership API rollout partners are pushing for real-time premium quotation at dealership; current scope is only VIN validation. | Rudi Hermawan | Medium | Open | 2026-01-25 | 2026-03-05 | Scope guardrail agreed with sponsor: Phase 1 VIN validation only; premium quote deferred to Phase 2.
I002 | Issue | Motor Platform performance under load | During peak load test the Motor Platform response time exceeded 2.5s at 800 concurrent users. Target is under 1.5s at 1200 users. | Budi Prasetyo | High | In Progress | 2026-02-08 | 2026-02-28 | DB query plan review with infra team; Redis cache layer added for policy lookup service.
R004 | Risk | Property policy issuance rework rate | For commercial property, 22 percent of policies are re-issued due to incomplete underwriting data at quote stage. | Sari Wulandari | High | Open | 2026-01-18 | 2026-04-15 | New pre-quote checklist deployed to brokers; underwriter STP rules being tuned in the new platform.
D002 | Dependency | OJK approval for Sharia product endorsement | Sharia Product Launch requires an OJK product registration confirmation before go-live. | Dewi Anggraini | High | Open | 2026-01-30 | 2026-03-30 | Submission filed 2026-02-01. Regulatory affairs tracks weekly.
A002 | Assumption | Leasing partner data feed is monthly | Assumption in Auto Manufacturer Partnership API rollout that leasing partners submit VIN feeds monthly. Some partners now request weekly. | Rudi Hermawan | Low | Closed | 2026-01-10 | 2026-01-31 | Confirmed monthly cadence with 5 of 6 partners; sixth accommodated via ad-hoc pull.
R005 | Risk | Marine Cargo underwriter shortage | Only 4 senior Marine Cargo underwriters in the country. Digital Onboarding pilot may overload them during ramp-up. | Andi Nugroho | Medium | Open | 2026-02-05 | 2026-04-01 | Automated pre-screen for standard risks; senior underwriter time reserved for complex cargo classes.
I003 | Issue | Bancassurance branch training attendance low | Only 55 percent of Bank BCA Syariah branches sent staff to the first two training webinars for the Bancassurance Distribution Integration. | Rina Kartika | Medium | In Progress | 2026-02-10 | 2026-03-01 | Third webinar rescheduled to Saturday morning; recorded on-demand version distributed via bank LMS.
R006 | Risk | Motor Platform vendor commercial change | Motor Platform core vendor announced a licence model change effective 2026-Q3, potentially adding 8 percent to run cost. | Budi Prasetyo | Medium | Open | 2026-02-12 | 2026-03-31 | Procurement negotiating rate-lock. Legal reviewing MSA change provisions.
D003 | Dependency | Property claims panel workshop network | New Property Platform requires the workshop and adjuster panel to accept digital job cards. 30 of 120 panel workshops not yet onboarded. | Sari Wulandari | Medium | In Progress | 2026-01-22 | 2026-03-20 | Field enablement squad on-site in Jakarta and Surabaya weekly. Digital job card training PDF distributed.
R007 | Risk | Earthquake exposure accumulation, Sharia portfolio | Sharia Product Launch initial portfolio includes earthquake-exposed commercial risks in West Java. Accumulation control needs review. | Dewi Anggraini | High | Open | 2026-01-28 | 2026-03-15 | CAT accumulation model refresh by 2026-03-01. Retrocession terms with reinsurer being confirmed.
I004 | Issue | Bancassurance premium reconciliation lag | Daily premium reconciliation with bancassurance partners is lagging by 3 to 4 days versus target of same day. | Rina Kartika | Medium | Open | 2026-02-11 | 2026-03-05 | Finance and vendor engineering pair-programming on payment file format; target same day by 2026-03-01.
A003 | Assumption | Auto manufacturer API stable versioning | Assume manufacturer APIs will remain on v2 through 2026. One partner has scheduled v3 for 2026-Q4. | Rudi Hermawan | Low | Open | 2026-02-14 | 2026-05-01 | Version negotiation with the partner; abstraction layer inserted in our adaptor.
R008 | Risk | Change fatigue in claims regional offices | Motor, Property and Marine claims teams across Jakarta, Surabaya and Medan are absorbing three parallel changes. | Sari Wulandari | Medium | Open | 2026-02-01 | 2026-03-31 | Change council pacing plan issued; Change Champion network in each regional office.
I005 | Issue | Marine Cargo broker portal single sign-on | Broker single sign-on to Marine Cargo Digital Onboarding portal is timing out for 8 percent of brokers. | Andi Nugroho | Medium | In Progress | 2026-02-13 | 2026-02-28 | Identity provider token TTL raised; retry logic added to portal.
R009 | Risk | Property Platform data privacy exposure | New Property Platform stores claimant KYC scans. Privacy Impact Assessment shows gaps in retention policy. | Sari Wulandari | High | Open | 2026-01-19 | 2026-03-01 | DPO leading PIA remediation. Retention automation targeted by 2026-02-28.
D004 | Dependency | Motor Platform integration with police reports | Motor Platform target STP for straight-forward accidents needs an API into the national police report system. | Budi Prasetyo | High | Open | 2026-02-03 | 2026-04-15 | MoU renewal with police IT department in progress; interim manual upload path retained.
A004 | Assumption | Bancassurance partner marketing calendar aligned | Assume bancassurance partners align their Q2 marketing calendar to the new integrated product journey. | Rina Kartika | Low | Open | 2026-02-06 | 2026-03-30 | Joint marketing sync scheduled monthly with each bancassurance partner.
I006 | Issue | Sharia UAT script gap for takaful contribution | UAT scripts for Sharia Product Launch do not yet cover contribution allocation between tabarru and ujrah accounts. | Dewi Anggraini | High | In Progress | 2026-02-09 | 2026-02-22 | Sharia SME pairing with QA to write scripts by 2026-02-19; regression added.
R010 | Risk | Auto manufacturer API PII handling | Vehicle telemetry may contain driver PII. Auto Manufacturer Partnership API rollout privacy control needs sign-off. | Rudi Hermawan | Medium | Open | 2026-02-15 | 2026-04-01 | PII masking library adopted; DPO review scheduled.
D005 | Dependency | Marine cargo reinsurance placement | Marine Cargo Digital Onboarding requires the new fac-obligatory treaty confirmed by reinsurer broker. | Andi Nugroho | High | In Progress | 2026-02-04 | 2026-03-10 | Broker submission complete 2026-02-11; treaty terms expected 2026-03-05.